## Project Information
Greenfields Respite, Barnstaple - Take-Off and Specification Summary
Project | Greenfields Respite Unit, Derby Rd, Barnstaple EX32 7EZ - main building external refurbishment: door & window replacement package (part of wider externals contract)
Client / CA | Devon County Council / South West Norse Ltd (spec 08-24-120619 Rev 1)
Main contractor | Pearce Construction - Neil Macilwaine, Surveyor/Estimator, 01271 852139, macilwaineN@pearceconstruction.co.uk
TENDER DEADLINE | 12 NOON, 17 JULY 2026 (quotation to Pearce)
Contract | JCT Minor Works 2024 (with amendments); commencement 31/08/2026; contract period 12 weeks; defects liability 12 months; LAD GBP250/wk; retention 5%; min insurance GBP5m
Site constraints | OPERATIONAL CARE HOME for young adults with learning disabilities - working-hour limits, close coordination with site staff (Nicola Griffiths 01271 343709), room-by-room sequencing, furniture moves by liaison, Schedule of Condition before starting
Quantities | 77 openings taken off drawing 005 P2: 58 uPVC windows (35 clear / 23 obscured incl. 17nr ~2375x1140 bathroom units), 4 aluminium screens (2 with NSHEV smoke vents), 15 doorsets (5 uPVC, 5 alu white, 5 alu brown RAL 8004). Ground 47 / First 28 / Full-height 2
Frame materials | uPVC (PVCu to BS7412/BS7413, reinforced) and powder-coated aluminium; internally AND externally WHITE except plant/boiler doors DG-03/04/06/07/08 in Brown RAL 8004
Thermal | Max U-value 1.4 W/m2K (whole window); thermally broken screens; trickle vents to Part F (equivalent area >= existing)
Glass spec | Safety glazing THROUGHOUT to BS6262/BS EN 12600, kitemarked every pane. Windows: TOUGHENED outer + LAMINATED inner (burglar resistance). Doors: toughened both panes. Obscure glass to WCs/bathrooms (23 windows). Clear elsewhere. Critical locations Part K4; class C BS6206 zones hatched on 005
Security ratings | Windows PAS 24:2022. Two-stage locking handles. Ground-floor restrictors; FIRST-FLOOR ESCAPE windows with restrictors + override button (Part B1); Jackloc Titan Folding Restrictor for pricing. Door controls: concealed maglocks tied to existing warning + key-card systems (interface works by specialist - see exclusions)
Fire/escape | Escape windows 1/20th floor area rule (3.10.33); fire exit doors: push pads (single) / push bars (double); DG-01 & DG-09 push pad + external pull handles; BS5499 signage both faces; NSHEV smoke vents in WG-01 + second stair screen connected to fire alarm
EPDM requirements | EPDM glazing gaskets with knock-in PVCu beads (internal beads preferred; security fixings if external); perimeter sealing PU foam/impregnated tape + sealant inside and out (3.10.39/3.11.6)
Hardware | Corrosion-resistant commercial grade (domestic quality NOT acceptable); 300-series stainless fixings; hardware fixed to reinforcement; friction stays to top-hung fanlights
Standards | BS 8213-4, BS6262, BS8000-7, GGF good practice, BS6375 Pt1 (wind 48 m/s SEVERE, 1200Pa), BS7412 + BS7413 approvals - EVIDENCE REQUIRED WITH TENDER; BS476 Pt7 Class 1 / EN 13501-1 Class B; frames marked with manufacturer/date/BS at ~1m centres
Install | FENSA-approved installer; prefabrication drawings for CA approval BEFORE manufacture; drawings + design calcs within 14 days of acceptance; plumb/level within 5mm per 2000mm; fixings at 600mm ctrs max, 150mm from corners; Kooltherm cavity closers; making good + PVCu trims; window bay posts checked/replaced where necessary (005 note)
Warranties | Installation 12 months; DGUs 10-year INSURANCE-BACKED guarantee; components 12 months; all registration costs included
Deadlines/programme | Tender 17/07/2026 noon; start on site 31/08/2026; 12-week overall contract - window works sequenced around operational home; survey dims final ('all dimensions for guidance, final measurements by manufacturer' - 005)
Manifestation | To Approved Docs M1/M2 2.24 and N2 on glazed doors/screens - included as allowance

## Window & Door Schedule
Ref | Floor | Width mm | Height mm | Material | Glass | Type | Qty | Area m2 | Features / ironmongery
WG-01 | GF-FF | 2709 | 5100 | Alu PPC white | clear | screen | 1 | 13.82 | Stair screen; 3nr NSHEV AOV top vents linked to fire alarm; 900mm render panel zone below
WG-33* | GF-FF | 1689 | 4590 | Alu PPC white | clear | screen | 1 | 7.75 | Stair screen; 2nr NSHEV AOV top vents linked to fire alarm (ref label unclear on 005 - RFI)
WG-31 | GF | 1447 | 2410 | Alu PPC white | clear | screen | 1 | 3.49 | Fanlight + fixed + lower panel; part of 4840 entrance screen with DG-11
WG-32 | GF | 1447 | 2410 | Alu PPC white | clear | screen | 1 | 3.49 | Fanlight + fixed + lower panel; part of 4840 entrance screen with DG-11
WG-02 | GF | 2372 | 1140 | uPVC white | obscured | win | 1 | 2.7 | Top-hung fanlight over fixed; obscure glazed
WG-03 | GF | 2372 | 1140 | uPVC white | obscured | win | 1 | 2.7 | Top-hung fanlight over fixed; obscure glazed
WG-04 | GF | 2378 | 1140 | uPVC white | obscured | win | 1 | 2.71 | Top-hung fanlight over fixed; obscure glazed
WG-05 | GF | 2378 | 1140 | uPVC white | obscured | win | 1 | 2.71 | Top-hung fanlight over fixed; obscure glazed
WG-06 | GF | 2378 | 1140 | uPVC white | obscured | win | 1 | 2.71 | Top-hung fanlight over fixed; obscure glazed
WG-07 | GF | 2372 | 1140 | uPVC white | obscured | win | 1 | 2.7 | Top-hung fanlight over fixed; obscure glazed
WG-08 | GF | 2372 | 1140 | uPVC white | obscured | win | 1 | 2.7 | Top-hung fanlight over fixed; obscure glazed
WG-10 | GF | 2372 | 1140 | uPVC white | obscured | win | 1 | 2.7 | Top-hung fanlight over fixed; obscure glazed
WF-01 | FF | 2372 | 1140 | uPVC white | obscured | win | 1 | 2.7 | Top-hung fanlight over fixed; obscure glazed
WF-02 | FF | 2372 | 1140 | uPVC white | obscured | win | 1 | 2.7 | Top-hung fanlight over fixed; obscure glazed
WF-03 | FF | 2378 | 1140 | uPVC white | obscured | win | 1 | 2.71 | Top-hung fanlight over fixed; obscure glazed
WF-04 | FF | 2378 | 1140 | uPVC white | obscured | win | 1 | 2.71 | Top-hung fanlight over fixed; obscure glazed
WF-05 | FF | 2378 | 1140 | uPVC white | obscured | win | 1 | 2.71 | Top-hung fanlight over fixed; obscure glazed
WF-06 | FF | 2372 | 1140 | uPVC white | obscured | win | 1 | 2.7 | Top-hung fanlight over fixed; obscure glazed
WF-07 | FF | 2378 | 1140 | uPVC white | obscured | win | 1 | 2.71 | Top-hung fanlight over fixed; obscure glazed
WF-08 | FF | 2372 | 1140 | uPVC white | obscured | win | 1 | 2.7 | Top-hung fanlight over fixed; obscure glazed
WF-09 | FF | 2372 | 1140 | uPVC white | obscured | win | 1 | 2.7 | Top-hung fanlight over fixed; obscure glazed
WG-09 | GF | 905 | 1150 | uPVC white | obscured | win | 1 | 1.04 | Top-hung over fixed; obscure glazed
WG-11 | GF | 825 | 975 | uPVC white | obscured | win | 1 | 0.8 | Single fixed/opener; obscure glazed
WG-41 | GF | 990 | 1120 | uPVC white | obscured | win | 1 | 1.11 | Top-hung over fixed; obscure glazed
WG-42 | GF | 990 | 1120 | uPVC white | obscured | win | 1 | 1.11 | Top-hung over fixed; obscure glazed
WF-19 | FF | 990 | 1120 | uPVC white | obscured | win | 1 | 1.11 | Top-hung over fixed; obscure glazed
WF-20 | FF | 990 | 1120 | uPVC white | obscured | win | 1 | 1.11 | Top-hung over fixed; obscure glazed
WG-13 | GF | 3108 | 500 | uPVC white | clear | win | 1 | 1.55 | High-level 5-pane strip; 2 top-hung openers
WG-14 | GF | 2300 | 1950 | uPVC white | clear | win | 1 | 4.49 | 6-pane with top-hung opener; 900mm render panel below
WG-34 | GF | 2765 | 1460 | uPVC white | clear | win | 1 | 4.04 | 2 top-hung openers + fixed; escape-capable
WG-35 | GF | 2765 | 1460 | uPVC white | clear | win | 1 | 4.04 | 2 top-hung openers + fixed; escape-capable
WG-36 | GF | 2765 | 1460 | uPVC white | clear | win | 1 | 4.04 | 2 top-hung openers + fixed; escape-capable
WG-37 | GF | 2765 | 1460 | uPVC white | clear | win | 1 | 4.04 | 2 top-hung openers + fixed; escape-capable
WG-38 | GF | 2765 | 1460 | uPVC white | clear | win | 1 | 4.04 | 2 top-hung openers + fixed; escape-capable
WG-39 | GF | 2765 | 1460 | uPVC white | clear | win | 1 | 4.04 | 2 top-hung openers + fixed; escape-capable
WF-12 | FF | 2765 | 1460 | uPVC white | clear | win | 1 | 4.04 | 2 top-hung openers + fixed; FIRST-FLOOR ESCAPE window - restrictor with override
WF-13 | FF | 2765 | 1460 | uPVC white | clear | win | 1 | 4.04 | 2 top-hung openers + fixed; FIRST-FLOOR ESCAPE window - restrictor with override
WF-14 | FF | 2765 | 1460 | uPVC white | clear | win | 1 | 4.04 | 2 top-hung openers + fixed; FIRST-FLOOR ESCAPE window - restrictor with override
WF-15 | FF | 2765 | 1460 | uPVC white | clear | win | 1 | 4.04 | 2 top-hung openers + fixed; FIRST-FLOOR ESCAPE window - restrictor with override
WF-16 | FF | 2765 | 1460 | uPVC white | clear | win | 1 | 4.04 | 2 top-hung openers + fixed; FIRST-FLOOR ESCAPE window - restrictor with override
WF-17 | FF | 2765 | 1460 | uPVC white | clear | win | 1 | 4.04 | 2 top-hung openers + fixed; FIRST-FLOOR ESCAPE window - restrictor with override
WG-40 | GF | 1360 | 1460 | uPVC white | clear | win | 1 | 1.99 | 2 top-hung openers over fixed
WF-18 | FF | 1360 | 1460 | uPVC white | clear | win | 1 | 1.99 | 2 top-hung openers over fixed; escape window
WG-43 | GF | 1484 | 1460 | uPVC white | clear | win | 1 | 2.17 | 2 openers over fixed
WG-45 | GF | 1484 | 1460 | uPVC white | clear | win | 1 | 2.17 | 2 openers over fixed
WG-46 | GF | 1484 | 1460 | uPVC white | clear | win | 1 | 2.17 | 2 openers over fixed
WG-47 | GF | 1484 | 1460 | uPVC white | clear | win | 1 | 2.17 | 2 openers over fixed
WG-48 | GF | 1484 | 1460 | uPVC white | clear | win | 1 | 2.17 | 2 openers over fixed
WG-49 | GF | 2238 | 1460 | uPVC white | clear | win | 1 | 3.27 | Openers + fixed; 950mm cladding panel below
WG-50 | GF | 2238 | 1460 | uPVC white | clear | win | 1 | 3.27 | Openers + fixed; 950mm cladding panel below
WF-21 | FF | 1455 | 1130 | uPVC white | clear | win | 1 | 1.64 | Opener + fixed; escape window with restrictor override
WF-23 | FF | 1455 | 1130 | uPVC white | clear | win | 1 | 1.64 | Opener + fixed; escape window with restrictor override
WF-24 | FF | 1455 | 1130 | uPVC white | clear | win | 1 | 1.64 | Opener + fixed; escape window with restrictor override
WF-25 | FF | 1455 | 1130 | uPVC white | clear | win | 1 | 1.64 | Opener + fixed; escape window with restrictor override
WF-26 | FF | 1455 | 1130 | uPVC white | clear | win | 1 | 1.64 | Opener + fixed; escape window with restrictor override
WF-27 | FF | 1338 | 1130 | uPVC white | clear | win | 1 | 1.51 | Openers over fixed; combo with door DF-02; 980mm cladding below
WF-28 | FF | 2238 | 1130 | uPVC white | clear | win | 1 | 2.53 | Fixed + opener; 980mm cladding panel below
WF-22 | FF | 1380 | 1470 | uPVC white | clear | win | 1 | 2.03 | In combo with DF-01 over 940mm cladding (ref also appears on a 1280x1500 elevation - RFI duplicate)
WF-22B* | FF | 1280 | 1500 | uPVC white | clear | win | 1 | 1.92 | Standalone elevation labelled WF-22 (duplicate ref - RFI; possibly WF-29)
WG-12 | GF | 1230 | 1300 | uPVC white | clear | win | 1 | 1.6 | Side-by-side with door DG-05
WG-44 | GF | 2210 | 1470 | uPVC white | clear | win | 1 | 3.25 | Openers + fixed over 940mm cladding; combo with DG-14
WG-30 | GF | 4989 | 1660 | uPVC white | clear | screen | 1 | 8.28 | 4-pane screen with top-hung openers; part of 6074 run with DG-10; 670mm render below; new posts
DG-05 | GF | 850 | 2200 | uPVC white | clear | door | 1 | 1.87 | Single door + lower panel; beside WG-12; latch + thumb turn; maglock interface
DG-10 | GF | 985 | 2330 | uPVC white | clear | door | 1 | 2.3 | Single door in WG-30 screen; latch + thumb turn; maglock interface
DG-14 | GF | 940 | 2410 | uPVC white | clear | door | 1 | 2.27 | Single FIRE EXIT door + fanlight; push pad; combo with WG-44
DF-01 | FF | 940 | 2410 | uPVC white | clear | door | 1 | 2.27 | Single FIRE EXIT door + fanlight; push pad; combo with WF-22
DF-02 | FF | 900 | 2330 | uPVC white | clear | door | 1 | 2.1 | Single FIRE EXIT door; push pad; combo with WF-27
DG-01 | GF | 910 | 2390 | Alu PPC white | clear | door | 1 | 2.17 | Single FIRE EXIT door + fanlight; push pad + external pull handle (spec 3.13); critical-location safety glass
DG-02 | GF | 750 | 2000 | Alu PPC white | clear | door | 1 | 1.5 | Single FIRE EXIT door (narrow); push pad; critical glass
DG-09 | GF | 2756 | 2330 | Alu PPC white | clear | door | 1 | 6.42 | MAIN ENTRANCE screen: door (min 1000mm clear opening) + side glazing + 'Greenfield's' fascia sign panel + letterbox; push pad + pull handles; maglock/key-card interface
DG-11 | GF | 1746 | 2410 | Alu PPC white | clear | door2 | 1 | 4.21 | DOUBLE FIRE EXIT door + fanlight in 4840 screen; push bars
DG-12 | GF | 1270 | 2410 | Alu PPC white | clear | door2 | 1 | 3.06 | DOUBLE (narrow pair) FIRE EXIT door + fanlight; push bars
DG-03 | GF | 1637 | 2400 | Alu PPC RAL 8004 | louvre | door2 | 1 | 3.93 | DOUBLE plant-room door with METAL LOUVRE panels + top vents; push pad + latch handle and lock; NO maglock
DG-04 | GF | 825 | 2100 | Alu PPC RAL 8004 | panel | door | 1 | 1.73 | Single FIRE EXIT door + lower panel; push pad + latch/lock; no maglock
DG-06 | GF | 949 | 2100 | Alu PPC RAL 8004 | panel | door | 1 | 1.99 | Single FIRE EXIT plant door + panel; push pad + latch/lock; no maglock
DG-07 | GF | 949 | 2100 | Alu PPC RAL 8004 | panel | door | 1 | 1.99 | Single FIRE EXIT plant door + panel; push pad + latch/lock; no maglock
DG-08 | GF | 2756 | 2680 | Alu PPC RAL 8004 | clear | slidefold | 1 | 7.39 | 3-LEAF SLIDE-FOLD door (amended P2); confirm operation/gear spec

## RFIs & Queries
# | Query for Pearce Construction / CA
1 | Drawing 005 shows no elevations for WG-15 to WG-29, WF-10/WF-11 or DG-13, yet the floor plans reference at least WG-27 and DG-13. Please confirm whether these openings are in the replacement scope and issue details.
2 | Ref WF-22 appears twice on drawing 005 (standalone 1280x1500 elevation AND within the DF-01 combo). Please confirm intended references.
3 | The second full-height aluminium NSHEV stair screen (1689 x 4590) has no legible ref on 005 - please confirm its reference.
4 | NSHEV smoke vents (WG-01 + second screen): we have allowed for AOV vents/actuators; please confirm who supplies controls and the fire-alarm connection (assumed by others/specialist).
5 | Door maglocks/key-card interface (spec 3.12): allowed as builders-work interface only; connection to existing warning/key-card systems assumed by the client's specialist under the GBP5,000 provisional sum (3.22.2). Please confirm.
6 | DG-08 3-leaf slide-fold (amended P2): please confirm operation (slide-fold vs sliding), threshold and gear spec.
7 | DG-09 'Greenfield's' fascia sign panel: please confirm sign supply (we have allowed a plain panel + allowance).
8 | Obscure glass pattern/privacy level to be confirmed (we allow standard stippolyte level 3).
9 | Access: main roofing scaffold by others assumed available where helpful; we allow tower access for window works only.