## Project Information
Redditch Library - Fenster take-off and benchmark price
Project | Redditch Library, 15 Market Place, Redditch, B98 8AR - flat roof refurbishment and external window and door replacement
Tender reference | BLBS0956, version 01, dated May 2026, 254 pages
End client | Worcestershire County Council
Contract administrator | Gleeds Cost Management Ltd, Birmingham - Shaun Wilkes BSc (Hons) MRICS, Director of Building Surveying
We are invited by | Pride Developments Group Ltd, Cwmbran - Leonard White, Senior Quantity Surveyor. Pride are bidding to Gleeds as main contractor; Fenster are their window and door sub-contractor.
Enquiry received | 22 July 2026 to info@, forwarded to Commercial@ and to Adam the same afternoon. Referred to estimating 28 July.
OUR DEADLINE | NOT SET. Leonard White asked on 22/07 to acknowledge and 'submit your tender back asap' and gave no date. The 12 noon, Friday 26 June 2026 in the pack is GLEEDS' date to the main contractors and it has passed. Our date is whatever Pride need and nobody has asked them.
Contract | JCT Minor Works with Contractor's Design Portion. 10 weeks to completion from commencement (TBC). Liquidated damages GBP 1,000 per calendar week. Retention 5%, releasing to 2.5% at practical completion. Rectification period six months. Public liability GBP 5m. CDP professional indemnity GBP 5m. No amendments to sections 3-7. The JCT form itself is not in the pack, and no sub-contract has been received from Pride.
Tender validity | 10 weeks from submission on the Form of Tender; 'not less than 3 months' in the preliminaries. Two figures, one pack - RFI-08.
Award criteria | 70% price, 30% quality. Lowest compliant tender scores 70.
Site constraints | OPERATIONAL PUBLIC LIBRARY, occupied throughout. Working hours Mon-Fri 08:30-18:00 in the Schedule of Works and 08:30-17:30 in the preliminaries. Windows may not be left out over a shift - removal and replacement within the same working day. Elevation A fronts a public highway. Window-by-window programme required, rooms inspected three working days ahead, photographs before works. FORS Gold required for vehicles. ONE tender site visit only, arranged through Gleeds with all sub-contractors present.
Quantities | 43 items across 41 references, 136.54 m2. Taken from the tender's OWN blank pricing schedule (pack p77) and cross-checked line by line against Joedan's Appendix 2 schedule (p150) - the two are identical in every size and configuration - and against elevational drawings BLBS0956-GLE-RL-XX-DR-B-02 and -B-03. All 41 references appear on the elevations; none is missing and none is duplicated.
Systems specified | Windows: EL75mm Squareline, polyester powder coated thermally broken aluminium. Doors: AC100 Commercial, polyester powder coated NON-THERMAL high traffic aluminium. BOTH ARE JOEDAN MANUFACTURING'S OWN SYSTEMS and Fenster cannot buy either. Specification 3.5.3 cl.3 expressly permits an alternative, subject to a compliance specification submitted WITH the tender return, written CA and Client approval, and the tenderer taking design responsibility under the Contractor's Designed Portion.
Thermal | Windows 1.4 W/m2K area weighted; doors 3.0 W/m2K area weighted; infill panels 1.2 W/m2K. The window and door figures are PACKAGE AVERAGES, not per-element limits. 3.0 on the doors is a non-thermal door - for once the specification is easier than the house system, which is 1.8 W/m2K.
Glass | Argon filled double glazed units with warm edge spacer. Inner pane 4mm clear soft coat low-E toughened. Outer pane 4mm BRONZE ANTI-SUN toughened. Safety glass to all Part K critical locations; transom and mullion heights to comply with Part K.
Warranty | Fenster ten years. Gleeds specify no warranty period for the windows and doors - the only warranty requirement in the pack is 25 years insurance-backed on the roofing, which is not our package. Joedan, pricing the same building, offered TWELVE MONTHS.
Asbestos | Bradley Environmental J449293, targeted R&D survey, 01/10/2025. All four window-related samples - mastic to metal framed windows, putty sealant, mastic to metal window frames, mastic to window joins, 75 linear metres - NO ASBESTOS DETECTED. But FM000125, asbestos bitumen paint to metal cladding, CHRYSOTILE, 100 m2, 'left hand elevation', easily disturbed, 'REMOVE if affected by scheduled work'. RFI-07. GBP 5,000 defined provisional sum in the pack covers the whole building including the roof.
Basis of this price | BENCHMARK ONLY. No supplier has been asked and no quotation is held - the Commercial archive holds one file for this job and it is the tender pack. Rates are Fenster's own charged rates where enough history exists (learned) and supplier-quote medians otherwise (register). Every line states which. THIS IS NOT A QUOTABLE PRICE.

## Window & Door Schedule
Ref | Elev | Width mm | Height mm | Area m2 | Type | Configuration per the tender schedule | Notes
1 | A | 1800 | 2000 | 3.6 | window | 1 fixed light + 1 fixed panel
2 | A | 1800 | 2000 | 3.6 | window | 1 fixed light + 1 fixed panel
3 | A | 2650 | 1800 | 4.77 | window | 2 fixed lights + 2 fixed panels
4 | A | 2650 | 1800 | 4.77 | window | 2 fixed lights + 2 fixed panels
5 | A | 2650 | 1800 | 4.77 | window | 2 fixed lights + 2 fixed panels
6 | A | 2650 | 1800 | 4.77 | window | 2 fixed lights + 2 fixed panels
7 | A | 2650 | 1800 | 4.77 | window | 2 fixed lights + 2 fixed panels
8 | A | 2650 | 1800 | 4.77 | window | 2 fixed lights + 2 fixed panels
9 | A | 2248 | 1600 | 3.597 | window | 2 top-hung opening lights
10 | A | 2248 | 1600 | 3.597 | window | 2 top-hung opening lights
11 | A | 2248 | 1600 | 3.597 | window | 2 top-hung opening lights
12 | A | 2248 | 1600 | 3.597 | window | 2 top-hung opening lights
13 | A | 2248 | 1600 | 3.597 | window | 2 top-hung opening lights
14 | A | 2248 | 1600 | 3.597 | window | 2 top-hung opening lights
15 | A | 900 | 1600 | 1.44 | window | 1 top-hung opening light
16 | A | 2250 | 2304 | 5.184 | window | 2 fixed lights + 2 fixed panels | RAKED - drawn as a parallelogram on the stair wall, sloping head and cill. 2250x2304 is a bounding box, not the frame. RFI-01.
17 | A | 2250 | 2304 | 5.184 | window | 2 fixed lights + 2 fixed panels | RAKED - as ref 16. RFI-01.
18 | A | 2250 | 2304 | 5.184 | window | 2 fixed lights + 2 fixed panels | RAKED - as ref 16. RFI-01.
19 | A | 17000 | 900 | 15.3 | window | 20 fixed lights | 17m continuous high-level ribbon over the whole of Elevation A. 20 bays counted on the drawing at 850mm centres - agrees with the schedule. Sits onto the flat roof: up-stand EXCLUDED.
20 | D | 7000 | 1100 | 7.7 | window | 7 fixed lights + 1 fixed panel | 7m high-level ribbon, Elevation D.
21 | D | 1200 | 1200 | 1.44 | window | 1 top-hung + 1 fixed light
22 | C | 1500 | 1000 | 1.5 | window | 1 fixed light
23 | C | 1500 | 1000 | 1.5 | window | 1 fixed light
24 | C | 900 | 525 | 0.473 | window | 1 top-hung opening light
25 | C | 900 | 525 | 0.473 | window | 1 top-hung opening light
26 | C | 900 | 525 | 0.473 | window | 1 top-hung opening light
27 | C | 900 | 525 | 0.473 | window | 1 top-hung opening light
28 | C | 900 | 525 | 0.473 | window | 1 top-hung opening light
29 | C | 900 | 300 | 0.27 | window | NOT STATED | Configuration BLANK on Gleeds' own schedule and on Joedan's. Priced as a fixed light - stated assumption. RFI-02.
30 | C | 900 | 300 | 0.27 | window | NOT STATED | Configuration BLANK on both schedules. Priced as a fixed light. RFI-02.
31 | C | 900 | 300 | 0.27 | window | NOT STATED | Configuration BLANK on both schedules. Priced as a fixed light. RFI-02.
32.1 | C | 1800 | 1600 | 2.88 | window | 1 top-hung + 1 fixed light + 1 fixed panel | COUPLED to door 32.2 as ONE assembly on the elevation. Priced in a single thermally broken system throughout - see RFI-03.
32.2 | C | 1170 | 2100 | 2.457 | door | single door | COUPLED to window 32.1. Panic set per spec cl.5. Priced in the same system as 32.1.
33 | C | 1800 | 1200 | 2.16 | window | 1 top-hung + 1 fixed light
34.1 | C | 2400 | 1600 | 3.84 | window | 1 top-hung + 2 fixed lights + 1 fixed panel | COUPLED to door 34.2 as ONE assembly on the elevation. Priced in a single thermally broken system - RFI-03.
34.2 | C | 900 | 2100 | 1.89 | door | single door | COUPLED to window 34.1. Panic set per spec cl.5.
35 | B | 1800 | 1200 | 2.16 | window | 1 top-hung + 1 fixed light
36 | B | 1800 | 1200 | 2.16 | window | 1 top-hung + 1 fixed light
37 | B | 1200 | 2100 | 2.52 | door | single door | Fire exit at roof level. Panic set per spec cl.5.
38 | C | 2700 | 1700 | 4.59 | window | 6 fixed lights | Drawn as a 5 x 3 = 15-PANE gridded screen; the schedule says 6 fixed lights. Framing content understated if the drawing is right. RFI-05.
39 | C | 1200 | 2100 | 2.52 | door | single door | The ONE door omitted from spec cl.5's ironmongery list (32, 34, 37, 41). No ironmongery specified anywhere. Priced as a plain single commercial doorset, NO panic set. RFI-06.
40 | C | 1200 | 1000 | 1.2 | window | 2 fixed lights
41 | B | 1500 | 2100 | 3.15 | door | double door | Double fire-exit door, Elevation B. Panic set + flush bolts to slave leaf per cl.5.
TOTAL |  |  |  | 136.54 | 43 items | 41 references; 32 and 34 each split in two

## Benchmark Price
Ref | Width mm | Height mm | Area m2 | Code | Rate GBP/m2 | Frame + adder | Fit labour | Basis | Where the rate comes from
1 | 1800 | 2000 | 3.6 | MAW | 467.57 | 2095.75 | 160 | REGISTER | aluminium casement window, glazed [3-6m2] median GBP467.57/m2 from 481 quote line(s) (bsw, 2025-2026)
2 | 1800 | 2000 | 3.6 | MAW | 467.57 | 2095.75 | 160 | REGISTER | aluminium casement window, glazed [3-6m2] median GBP467.57/m2 from 481 quote line(s) (bsw, 2025-2026)
3 | 2650 | 1800 | 4.77 | MAW | 467.57 | 2642.81 | 160 | REGISTER | aluminium casement window, glazed [3-6m2] median GBP467.57/m2 from 481 quote line(s) (bsw, 2025-2026)
4 | 2650 | 1800 | 4.77 | MAW | 467.57 | 2642.81 | 160 | REGISTER | aluminium casement window, glazed [3-6m2] median GBP467.57/m2 from 481 quote line(s) (bsw, 2025-2026)
5 | 2650 | 1800 | 4.77 | MAW | 467.57 | 2642.81 | 160 | REGISTER | aluminium casement window, glazed [3-6m2] median GBP467.57/m2 from 481 quote line(s) (bsw, 2025-2026)
6 | 2650 | 1800 | 4.77 | MAW | 467.57 | 2642.81 | 160 | REGISTER | aluminium casement window, glazed [3-6m2] median GBP467.57/m2 from 481 quote line(s) (bsw, 2025-2026)
7 | 2650 | 1800 | 4.77 | MAW | 467.57 | 2642.81 | 160 | REGISTER | aluminium casement window, glazed [3-6m2] median GBP467.57/m2 from 481 quote line(s) (bsw, 2025-2026)
8 | 2650 | 1800 | 4.77 | MAW | 467.57 | 2642.81 | 160 | REGISTER | aluminium casement window, glazed [3-6m2] median GBP467.57/m2 from 481 quote line(s) (bsw, 2025-2026)
9 | 2248 | 1600 | 3.597 | MAW | 467.57 | 2094.26 | 160 | REGISTER | aluminium casement window, glazed [3-6m2] median GBP467.57/m2 from 481 quote line(s) (bsw, 2025-2026)
10 | 2248 | 1600 | 3.597 | MAW | 467.57 | 2094.26 | 160 | REGISTER | aluminium casement window, glazed [3-6m2] median GBP467.57/m2 from 481 quote line(s) (bsw, 2025-2026)
11 | 2248 | 1600 | 3.597 | MAW | 467.57 | 2094.26 | 160 | REGISTER | aluminium casement window, glazed [3-6m2] median GBP467.57/m2 from 481 quote line(s) (bsw, 2025-2026)
12 | 2248 | 1600 | 3.597 | MAW | 467.57 | 2094.26 | 160 | REGISTER | aluminium casement window, glazed [3-6m2] median GBP467.57/m2 from 481 quote line(s) (bsw, 2025-2026)
13 | 2248 | 1600 | 3.597 | MAW | 467.57 | 2094.26 | 160 | REGISTER | aluminium casement window, glazed [3-6m2] median GBP467.57/m2 from 481 quote line(s) (bsw, 2025-2026)
14 | 2248 | 1600 | 3.597 | MAW | 467.57 | 2094.26 | 160 | REGISTER | aluminium casement window, glazed [3-6m2] median GBP467.57/m2 from 481 quote line(s) (bsw, 2025-2026)
15 | 900 | 1600 | 1.44 | SAW | 498.05 | 1054.69 | 160 | LEARNED | GBP498.05/m2 - median of 50 line(s) Fenster actually charged for SAW¦<1.5m2 (range 226.68-842.01), mined from sent pricing documents
16 | 2250 | 2304 | 5.184 | MAW | 467.57 | 2836.38 | 160 | REGISTER | aluminium casement window, glazed [3-6m2] median GBP467.57/m2 from 481 quote line(s) (bsw, 2025-2026)
17 | 2250 | 2304 | 5.184 | MAW | 467.57 | 2836.38 | 160 | REGISTER | aluminium casement window, glazed [3-6m2] median GBP467.57/m2 from 481 quote line(s) (bsw, 2025-2026)
18 | 2250 | 2304 | 5.184 | MAW | 467.57 | 2836.38 | 160 | REGISTER | aluminium casement window, glazed [3-6m2] median GBP467.57/m2 from 481 quote line(s) (bsw, 2025-2026)
19 | 17000 | 900 | 15.3 | ELAW | 344 | 5900.7 | 250 | LEARNED | GBP344.00/m2 - median of 15 line(s) Fenster actually charged for ELAW¦>6m2 (range 262.54-538.67), mined from sent pricing documents
20 | 7000 | 1100 | 7.7 | LAW | 365.18 | 3299.39 | 160 | REGISTER | aluminium casement window, glazed [>6m2] median GBP365.18/m2 from 82 quote line(s) (bsw, 2025-2026)
21 | 1200 | 1200 | 1.44 | SAW | 498.05 | 1054.69 | 160 | LEARNED | GBP498.05/m2 - median of 50 line(s) Fenster actually charged for SAW¦<1.5m2 (range 226.68-842.01), mined from sent pricing documents
22 | 1500 | 1000 | 1.5 | SAW | 363.5 | 882.75 | 160 | REGISTER | aluminium casement window, glazed [1.5-3m2] median GBP363.50/m2 from 446 quote line(s) (bsw, 2025-2026)
23 | 1500 | 1000 | 1.5 | SAW | 363.5 | 882.75 | 160 | REGISTER | aluminium casement window, glazed [1.5-3m2] median GBP363.50/m2 from 446 quote line(s) (bsw, 2025-2026)
24 | 900 | 525 | 0.473 | SAW | 498.05 | 572.83 | 160 | LEARNED | GBP498.05/m2 - median of 50 line(s) Fenster actually charged for SAW¦<1.5m2 (range 226.68-842.01), mined from sent pricing documents
25 | 900 | 525 | 0.473 | SAW | 498.05 | 572.83 | 160 | LEARNED | GBP498.05/m2 - median of 50 line(s) Fenster actually charged for SAW¦<1.5m2 (range 226.68-842.01), mined from sent pricing documents
26 | 900 | 525 | 0.473 | SAW | 498.05 | 572.83 | 160 | LEARNED | GBP498.05/m2 - median of 50 line(s) Fenster actually charged for SAW¦<1.5m2 (range 226.68-842.01), mined from sent pricing documents
27 | 900 | 525 | 0.473 | SAW | 498.05 | 572.83 | 160 | LEARNED | GBP498.05/m2 - median of 50 line(s) Fenster actually charged for SAW¦<1.5m2 (range 226.68-842.01), mined from sent pricing documents
28 | 900 | 525 | 0.473 | SAW | 498.05 | 572.83 | 160 | LEARNED | GBP498.05/m2 - median of 50 line(s) Fenster actually charged for SAW¦<1.5m2 (range 226.68-842.01), mined from sent pricing documents
29 | 900 | 300 | 0.27 | SAW | 498.05 | 471.97 | 160 | LEARNED | GBP498.05/m2 - median of 50 line(s) Fenster actually charged for SAW¦<1.5m2 (range 226.68-842.01), mined from sent pricing documents
30 | 900 | 300 | 0.27 | SAW | 498.05 | 471.97 | 160 | LEARNED | GBP498.05/m2 - median of 50 line(s) Fenster actually charged for SAW¦<1.5m2 (range 226.68-842.01), mined from sent pricing documents
31 | 900 | 300 | 0.27 | SAW | 498.05 | 471.97 | 160 | LEARNED | GBP498.05/m2 - median of 50 line(s) Fenster actually charged for SAW¦<1.5m2 (range 226.68-842.01), mined from sent pricing documents
32.1 | 1800 | 1600 | 2.88 | MAW | 347.74 | 1413.99 | 160 | LEARNED | GBP347.74/m2 - median of 39 line(s) Fenster actually charged for MAW¦1.5-3m2 (range 218.90-868.28), mined from sent pricing documents
32.2 | 1170 | 2100 | 2.457 | SAD | 490.13 | 2104.25 | 250 | LEARNED | GBP490.13/m2 - median of 64 line(s) Fenster actually charged for SAD¦1.5-3m2 (range 218.90-1474.51), mined from sent pricing documents
33 | 1800 | 1200 | 2.16 | SAW | 363.5 | 1122.66 | 160 | REGISTER | aluminium casement window, glazed [1.5-3m2] median GBP363.50/m2 from 446 quote line(s) (bsw, 2025-2026)
34.1 | 2400 | 1600 | 3.84 | MAW | 467.57 | 2207.97 | 160 | REGISTER | aluminium casement window, glazed [3-6m2] median GBP467.57/m2 from 481 quote line(s) (bsw, 2025-2026)
34.2 | 900 | 2100 | 1.89 | SAD | 490.13 | 1826.35 | 250 | LEARNED | GBP490.13/m2 - median of 64 line(s) Fenster actually charged for SAD¦1.5-3m2 (range 218.90-1474.51), mined from sent pricing documents
35 | 1800 | 1200 | 2.16 | SAW | 363.5 | 1122.66 | 160 | REGISTER | aluminium casement window, glazed [1.5-3m2] median GBP363.50/m2 from 446 quote line(s) (bsw, 2025-2026)
36 | 1800 | 1200 | 2.16 | SAW | 363.5 | 1122.66 | 160 | REGISTER | aluminium casement window, glazed [1.5-3m2] median GBP363.50/m2 from 446 quote line(s) (bsw, 2025-2026)
37 | 1200 | 2100 | 2.52 | SAD | 490.13 | 2135.13 | 250 | LEARNED | GBP490.13/m2 - median of 64 line(s) Fenster actually charged for SAD¦1.5-3m2 (range 218.90-1474.51), mined from sent pricing documents
38 | 2700 | 1700 | 4.59 | MAW | 467.57 | 2558.65 | 160 | REGISTER | aluminium casement window, glazed [3-6m2] median GBP467.57/m2 from 481 quote line(s) (bsw, 2025-2026)
39 | 1200 | 2100 | 2.52 | SAD | 490.13 | 2135.13 | 250 | LEARNED | GBP490.13/m2 - median of 64 line(s) Fenster actually charged for SAD¦1.5-3m2 (range 218.90-1474.51), mined from sent pricing documents
40 | 1200 | 1000 | 1.2 | SAW | 498.05 | 935.16 | 160 | LEARNED | GBP498.05/m2 - median of 50 line(s) Fenster actually charged for SAW¦<1.5m2 (range 226.68-842.01), mined from sent pricing documents
41 | 1500 | 2100 | 3.15 | DAD | 559.86 | 3263.56 | 500 | LEARNED | GBP559.86/m2 - median of 54 line(s) Fenster actually charged for DAD¦3-6m2 (range 135.63-1641.53), mined from sent pricing documents
Frames and code adders | [5 empty] | 80426.26 |  |  | Supply at the benchmark rate, plus the house template's code adder at 75% of code value.
Installation (FIT ONLY) | [5 empty] | 7670 |  |  | Adam's labour codes. These are fit rates and contain no strip-out - proven on Princess Beatrice and Brocks Hill.
Solar control glass premium | [5 empty] | 1814.56 |  |  | 136.54 m2 x GBP 13.29/m2. The specified outer pane is 4mm BRONZE ANTI-SUN; the frame rates above are built from ordinary softcoat units. Register glass medians: solar control toughened GBP 103.03/m2 against plain toughened softcoat GBP 89.74/m2.
BENCHMARK NET, EX VAT | [5 empty] | 89910.82 |  |  | NOT A QUOTABLE PRICE - no supplier has been asked.
NOT IN THE ABOVE
Strip out existing windows and doors | [5 empty] | TBC |  |  | Gleeds ask for this as a separate priced line (pack p70). NO RATE EXISTS ANYWHERE IN FENSTER'S RECORDS. The installation figure above is fit-only. This must be answered before a tender goes to Pride.
Provisional sum - preparing openings | [5 empty] | 5000 |  |  | Gleeds specification 3.5.3 cl.10, defined provisional sum, to be used as directed by the CA.
HOW THIS COMPARES
Joedan JCQ.9727, 23/03/2026 | [5 empty] | 90687.17 |  |  | The competitor's fully priced schedule, left in the tender pack at Appendix 2. Gross of 2.5% main contractor's discount, so GBP 88,419.99 net to a main contractor. NOT LIKE FOR LIKE: Joedan's figure INCLUDES strip-out (their cl.12) and ours excludes it, so on the same scope we are already above them.
Band-corrected sensitivity | [5 empty] | 79047.55 |  |  | The same take-off with the register's known band errors applied to the supply component (St Mary's calibration: -35.5% under 1.5 m2, -1.2% at 1.5-3, +37.5% at 3-6, +35.2% over 6). 62% of this job's value sits in the 3-6 m2 band where the register runs high, so the headline above is more likely high than accurate.

## Inclusions & Exclusions
INCLUDED
Supply and installation of 43no replacement aluminium windows and doors, refs 1-41 (32 and 34 each in two parts), to the sizes on the tender schedule.
Polyester powder coated thermally broken aluminium windows, single standard RAL internally and externally.
Commercial aluminium doorsets to refs 32.2, 34.2, 37, 39 and 41.
Argon filled double glazed units, warm edge spacer, 4mm clear soft coat low-E toughened inner pane, 4mm bronze anti-sun toughened outer pane.
Safety glass to all critical locations as defined by Part K.
Solid phenolic core infill panels faced both sides in 2.0mm matt PPC aluminium, 1.2 W/m2K.
Shootbolt espagnolette locking, Securistyle Defender friction hinges, concealed 100mm restrictors where required.
Trickle ventilators to all casements.
Panic ironmongery to doors 32, 34, 37 and 41 per specification cl.5 - Axim 8800 concealed transom closer, PR7100 exit panic device without external access, anti-finger-trap stiles, 100mm bottom and mid rails, mill finished low threshold, flush bolts to the slave leaf of ref 41.
45mm white cellular uPVC cloaking profile to the internal perimeter where required.
External grade waterproof mastic sealant to all windows and doors, applied at the time of installation.
One site visit to undertake the manufacturing survey.
Provisional sum of GBP 5,000 for preparing out-of-square openings, per specification cl.10.
Fenster's standard ten year guarantee.
EXCLUDED | Why / where it comes from
Strip out of the existing windows and doors, and carting debris off site | NOT PRICED - NO RATE EXISTS. Gleeds ask for this as a separate line on p70 of the pack ('Cost for stripping out windows'). Fenster's installation rates are FIT ONLY - proven on Princess Beatrice and on Brocks Hill, a new build with nothing to remove, which recompute to the penny from the same per-unit codes. There is no strip-out rate in the rate register. THIS MUST BE PRICED BEFORE ANYTHING GOES TO PRIDE.
Making good internally, including localised decoration to all reveals | Specification cl.11. Building trade, not glazing.
Removal, marking up, storage and re-fixing of internal blinds and curtains | Strip Out cl.6.
Moving furniture and equipment, dust sheeting and protection of retained items | Strip Out cl.5 and cl.7.
All access equipment - scaffolding, towers, podiums, MEWPs, hoisting and lifting equipment, and the temporary works design for it | Specification 3.4. Joedan excluded the same. Note refs 19, 35, 36, 37 and 41 are at high level or roof level.
Site set-up, Heras fencing, compound, hoardings, and protection to the Elevation A public highway frontage | Specification 3.2.
Flat roof covering replacement and all associated roofing work | Appendix 1, Alumasc. Not our package - windows and doors only.
Edge protection guard rail to the flat roof | Specification 3.5.2.
General repair and reinstatement - boxing in at roof level, rainwater goods, brickwork repairs | Specification 3.5.4.
Up-stand where windows sit onto the flat roof | Refs 19, 35, 36 and 37 sit at roof level. Joedan excluded the same item.
Building Control, skips, secure containers, welfare facilities, internal window boards, manifestations, fire signage, mag locks, door restraints, asbestos removal, and the moving of services, extractor fans, alarms or keypads | Standard exclusions, and all matched by Joedan's own exclusion list.

## RFIs & Queries
# | Query for Pride Developments, to be passed to Gleeds
RFI-01 | Refs 16, 17 and 18 are drawn on Elevation A as PARALLELOGRAMS following the stair soffit - sloping head and sloping cill - but scheduled as 2250 x 2304 rectangles, identically, all three. Please confirm the true frame geometry and the rake angle. A raked frame needs angled cuts to head, cill and both mullions and cannot be priced off a rectangle; the scheduled area also overstates the glass and understates the fabrication. GBP 8,509 of this take-off sits on these three.
RFI-02 | Refs 29, 30 and 31 (900 x 300) have EVERY configuration column blank on the tender's own pricing schedule as well as on Appendix 2. Please confirm what these three units are. They are priced here as fixed lights, which is the cheapest compliant reading; opening vents or louvres would change the price.
RFI-03 | Refs 32 and 34 are each drawn as ONE coupled assembly - a window frame joined directly to a door frame - but the specification puts the windows in EL75mm Squareline (thermally broken, 75mm) and the doors in AC100 Commercial (non-thermal, 100mm). Frames of different depths cannot be coupled. As written the specification cannot be built at these two positions. Please confirm which of the following is intended: (a) a thermally broken door so the whole run is one system and one depth; (b) a structural mullion or expressed movement joint between window and door so they are two separate frames; or (c) the window taken into the door system, which would put refs 32.1 and 34.1 outside the 1.4 W/m2K window requirement. This take-off assumes (a).
RFI-04 | Specification 3.5.3 cl.6 requires 'a single standard RAL colours TBC'. Please confirm the RAL number. Priced on one standard RAL both faces; a non-standard, metallic or anodised finish is an extra.
RFI-05 | Ref 38 (2700 x 1700) is drawn on Elevation C as a 5-wide by 3-high grid - 15 panes - and scheduled as 6 fixed lights. Please confirm the mullion and transom arrangement. Four mullions and two transoms is not the same frame as 6 lights.
RFI-06 | Specification 3.5.3 cl.5 lists the ironmongery for doors 32, 34, 37 and 41. Ref 39 is a fifth door and appears nowhere in that clause. Please confirm its ironmongery, whether it is a fire escape, and whether it is glazed - it is drawn as a solid narrow leaf. It is priced here as a plain single commercial doorset with no panic hardware.
RFI-07 | Asbestos survey J449293 sample FM000125 records asbestos bitumen paint to metal cladding, chrysotile, 100 m2, 'present to left hand elevation', accessibility 2 (easily disturbed), with the recommendation 'REMOVE if affected by scheduled work'. Please confirm which elevation is 'left hand' and whether the window replacement disturbs that cladding. If it is the raking wall carrying refs 16, 17 and 18 then the window strip-out disturbs it. Note the four window-specific samples (FM000123, 124, 126, 127 - mastic and putty to the metal window frames, 75 linear metres) all returned NO ASBESTOS DETECTED. Asbestos removal is excluded from this take-off.
RFI-08 | The Form of Tender holds the tendered sum open for 10 WEEKS from submission; the JCT Minor Works preliminaries separately require the tender to be kept open 'for not less than 3 months'. Please confirm which period governs. Aluminium supplier quotations are firm for 30 days, so either period leaves the buy uncovered for 5 to 10 weeks after we commit.
RFI-09 | Specification 3.5.3 cl.3 places the design of any alternative window system on the tenderer under the Contractor's Designed Portion, and the preliminaries require GBP 5,000,000 professional indemnity for Contractor Designed Works - stating BOTH '12 years' and 'Six years' for the expiry of the required period. Please confirm which. Please also confirm the form and level of detail required for the compliance specification, which the specification requires to be submitted WITH the tender return rather than after award.
RFI-10 | The invitation allows the tendering contractor ONE site visit, arranged through Gleeds, with all sub-contractors in attendance. Specification 3.5.3 separately requires a measured survey of every window and external door before ordering and states that Gleeds' dimensions must not be relied on. Please confirm whether a further access visit is available to the successful window contractor before ordering, or whether the measured survey is a post-award obligation to be programmed within the 10-week contract period.
NOTE | The invitation requires technical queries to be returned to Gleeds and assessed under the JCT Tendering Practice Note, 3rd Edition 2017. As sub-contractor our queries go through Pride.